## Risk Table
Risk Assessment Table
Hazard | Avoidance actions | Reduction actions | Acceptance actions | Probability | Impact
Insufficient time | Stick to plan Prioritise important tasks. | None | Not acceptable; must be prevented and will be monitored. | 7 | 8
Failure of the development hardware | Monitor health status of HW | None | Secondary equipment available. | 5 | 8
Loss of data | Everyday backup. | Constant sync with cloud. | Not acceptable. | 4 | 8
Physical destruction of all backups. (E.g. natural catastrophy) | Distribute backup to different locations. | None. | Not acceptable. | 2 | 9
"Failure by design" | Get exptert opinion on planing. | Increase planning time. | Decrease functionality or non functional parts of project. | 3 | 7
Problems while presentation. | Test presentation bevor actual presentation. | Good preperation for the presentation. | Not acceptable. | 5 | 7
Additional functionality during programming phase. | None. | Build program modular. | No inclusion of the additional features. | 2 | 4
Inhouse standards not met | Care for customer standards early | Verify whether adjustments possible | Low probability thus actions are taken at short notice | 3 | 6
Corruption of a single file. | Backup of all files. | None. | Rebuild of the single file. | 3 | 3

## Risk Assessment Map
Probability